## Schedule
QA Test Schedule
Content Area Assignments Per Full Sweep |  |  |  | Full Sweep Status
Content Type | Testing Date | Assigned To | Time Needed (Days) | Full Test Cycles | Status | Pass | Fail | Other
Armour | Week 1 | Tester 1 | 1 | Month 1 | Completed | 10% | 5% | 80%
Body | Week 1 | Tester 1 | 1 | Month 2 | Completed | 15% | 10% | 75%
Environment | Week 1 | Tester 1 | 3 | Month 3 | Completed | 20% | 8% | 72%
Footstep | Week 2 | Tester 1 | 2 | Month 4 | Completed | 40% | 10% | 50%
Magic | Week 2 | Tester 1 | 1 | Month 5 | Completed | 80% | 5% | 15%
Music | Week 4 | Tester 1 | 3 | Month 6 - ALPHA | Completed | 84% | 7% | 9%
VO | Week 4 | Tester 1 | 3 | Month 7 | Completed | 90% | 4% | 5%
Vocal | Week 3 | Tester 1 | 3 | Month 8 - BETA | Completed | 90.74% | 0% | 9.26%
UI | Week 3 | Tester 1 | 2 | Month 9 - FINAL | In Progress
Weapons | Week 2 | Tester 1 | 2

## Global Status
Overall Status
Overall Pass % (including N/A) |  |  |  | 93.67%
Overall Fail % (incl: blocked, Not Imp) |  |  |  | 0%
Overall Not Tested (Including Pending) |  |  |  | 6.333%
Project | CUBE | Overall Not Tested % |  | 0%
Overall Pending % | 6.333% | Overall Blocked % |  | 0%
Overall Pass % | 84.45% | Overall Not Implemented % |  | 0%
Overall Fail % | 0% | Overall N/A % |  | 9.217%
Content Area Status
Content Type | Status | Pending | Pass % | Fail % | Not Tested | Blocked | Not Implemented | N/A
Armour | Completed | 0% | 100% | 0% | 0% | 0% | 0% | 0%
Body | Completed | 0% | 95.65% | 0% | 0% | 0% | 0% | 4.348%
Environment | Completed | 0% | 62.59% | 0% | 0% | 0% | 0% | 37.41%
Footstep | Completed | 0% | 100% | 0% | 0% | 0% | 0% | 0%
Magic | Completed | 0% | 81.25% | 0% | 0% | 0% | 0% | 18.75%
Music | In Progress | 63.33% | 30% | 0% | 0% | 0% | 0% | 6.667%
VO | Completed | 0% | 100% | 0% | 0% | 0% | 0% | 0%
Vocal | Completed | 0% | 100% | 0% | 0% | 0% | 0% | 0%
UI | Completed | 0% | 75% | 0% | 0% | 0% | 0% | 25%
Weapons | Completed | 0% | 100% | 0% | 0% | 0% | 0% | 0%

## Armour
Armour
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 7 | 100%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 0 | 0%
TOTAL | 7
Entity Type | Content | Status | Bug No | Tested By | Comments
Leather
Player | Armour_Leather_Torso_Fast | Passed
Ogre | Armour_Leather_Torso_Fast | Passed
Slith | Armour_Leather_Torso_Fast | Passed
Bauul | Armour_Leather_Torso_Fast | Passed
Cloth
Ratamahatta | Armour_Cloth_Torso_Fast | Passed
Segmented
Knight | Armour_Metal_Plate_Torso_Fast | Passed
Mechanical
Rhino | Armour_Mechanical_Torso_Fast | Passed

## Body
Body
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 66 | 95.65%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 3 | 4.348%
TOTAL | 69
Entity Type | Content | Status | Bug No. | Comments
Body Impact
| Body_Impact_Leather | Passed
| Body_Impact_Segmented | N/A |  | On triggers on Player character (Leather)
| Body_Impact_Cloth | N/A |  | On triggers on Player character (Leather)
| Body_Impact_Metal | N/A |  | On triggers on Player character (Leather)
Body Land
| Body_Land_Humanoid_Leather_Concrete | Passed
| Body_Land_Humanoid_Leather_Grass | Passed
| Body_Land_Humanoid_Leather_Metal | Passed
| Body_Land_Humanoid_Leather_Sand | Passed
| Body_Land_Humanoid_Leather_Rock | Passed
| Body_Land_Humanoid_Leather_Stone | Passed
| Body_Land_Humanoid_Leather_Peddles | Passed
| Body_Land_Humanoid_Leather_Water | Passed
| Body_Land_Humanoid_Leather_Wood | Passed
| Body_Land_Humanoid_Leather_Undergrowth | Passed
Body Fall
| Body_Fall_Humanoid_Generic_Water | Passed
| Body_Fall_Humanoid_Segmented_Concrete | Passed
| Body_Fall_Humanoid_Segmented_Grass | Passed
| Body_Fall_Humanoid_Segmented_Metal | Passed
| Body_Fall_Humanoid_Segmented_Sand | Passed
| Body_Fall_Humanoid_Segmented_Rock | Passed
| Body_Fall_Humanoid_Segmented_Stone | Passed
| Body_Fall_Humanoid_Segmented_Water | Passed
| Body_Fall_Humanoid_Segmented_Wood | Passed
| Body_Fall_Humanoid_Segmented_Undergrowth | Passed
| Body_Fall_Humanoid_Segmented_Peddles | Passed
| Body_Fall_Humanoid_Leather_Concrete | Passed
| Body_Fall_Humanoid_Leather_Grass | Passed
| Body_Fall_Humanoid_Leather_Metal | Passed
| Body_Fall_Humanoid_Leather_Sand | Passed
| Body_Fall_Humanoid_Leather_Rock | Passed
| Body_Fall_Humanoid_Leather_Stone | Passed
| Body_Fall_Humanoid_Leather_Water | Passed
| Body_Fall_Humanoid_Leather_Wood | Passed
| Body_Fall_Humanoid_Leather_Undergrowth | Passed
| Body_Fall_Humanoid_Leather_Pebbles | Passed
| Body_Fall_Bauul_Flesh_Generic_Close | Passed
| Body_Fall_Bauul_Flesh_Generic_Far | Passed
| Body_Fall_Bauul_Flesh_Water_Close | Passed
| Body_Fall_Bauul_Flesh_Water_Far | Passed
| Body_Fall_Hellpig_Flesh_Concrete | Passed
| Body_Fall_Hellpig_Flesh_Grass | Passed
| Body_Fall_Hellpig_Flesh_Metal | Passed
| Body_Fall_Hellpig_Flesh_Sand | Passed
| Body_Fall_Hellpig_Flesh_Rock | Passed
| Body_Fall_Hellpig_Flesh_Stone | Passed
| Body_Fall_Hellpig_Flesh_Water | Passed
| Body_Fall_Hellpig_Flesh_Wood | Passed
| Body_Fall_Hellpig_Flesh_Undergrowth | Passed
| Body_Fall_Hellpig_Flesh_Pebbles | Passed
| Body_Fall_Rhino_Flesh_Concrete | Passed
| Body_Fall_Rhino_Flesh_Grass | Passed
| Body_Fall_Rhino_Flesh_Metal | Passed
| Body_Fall_Rhino_Flesh_Sand | Passed
| Body_Fall_Rhino_Flesh_Rock | Passed
| Body_Fall_Rhino_Flesh_Stone | Passed
| Body_Fall_Rhino_Flesh_Water | Passed
| Body_Fall_Rhino_Flesh_Wood | Passed
| Body_Fall_Rhino_Flesh_Undergrowth | Passed
| Body_Fall_Rhino_Flesh_Pebbles | Passed
Shield Drop
| Weaponary_Shield_Metal_Drop_Rest_Concrete | Passed
| Weaponary_Shield_Metal_Drop_Rest_Grass | Passed
| Weaponary_Shield_Metal_Drop_Rest_Metal | Passed
| Weaponary_Shield_Metal_Drop_Rest_Sand | Passed
| Weaponary_Shield_Metal_Drop_Rest_Rock | Passed
| Weaponary_Shield_Metal_Drop_Rest_Pebbles | Passed
| Weaponary_Shield_Metal_Drop_Rest_Water | Passed
| Weaponary_Shield_Metal_Drop_Rest_Wood | Passed
| Weaponary_Shield_Metal_Drop_Rest_Undergrowth | Passed
| Weaponary_Shield_Metal_Drop_Rest_Stone | Passed

## Environment
Environments
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 261 | 62.59%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 156 | 37.41%
TOTAL | 417
Map |  | Status |  |  |  | QA
MapType | Map Name | Surface Type | Environment Type | Reverb Heard | Advisor Intro | Bug No. | Tested By | Environment Event Name | Comments
Load Map | metl3 | Passed | Passed | Passed | Passed |  |  | ENV_Desert_Generic | Inside / outside area
| frag | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Warm | Castle Ruins Wind strength based on height
| ogrosupply | Passed | Passed | Passed | Passed |  |  | ENV_Warehouse_Warm | Inside/outside areas
| powerplant | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Generic | BLOCKED Centre map, open ceiling wind
| aquae | Passed | Passed | Passed | Passed |  |  | ENV_Normal_Generic | Inside/outside areas - BLOCKED River in middle of map
| drianmp3 | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Generic | Inside/outside areas
| douze | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | Castle Ruins Inside / outside areas
| kmap5 | Passed | Passed | Passed | Passed |  |  | ENV_Night_Water | CHANGED WATER HEIGHT - DOWN BY ONE, so player is actually underwater Inside / outside Map filled with above hip water
| q3dm2 | Passed | Passed | Passed | Passed |  |  | ENV_Mountain_Cold | CHANGED WATER AREA HEIGHT - DOWN BY ONE - so player is actually under water Castle Ruins - Inside/outside area
| uf | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Warm | NO XML Script Inside / Outside area
| mak1 | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Warm | Castle Ruins - Inside / otside area
| kmap6 | Passed | Passed | Passed | Passed |  |  | ENV_Night_Generic | indoor / outdoor areas Unique map textures? Kurt\ktrim_b + kurt\ktrim2_b + kurt\ktrim_corner_1
| metl2 | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Generic | Castle Ruins Inside/Outside areas
| mak2 | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Warm | Inside castle
Load Map > More Maps (1) | Caged | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Warm | .CFG removed music fanatic/revenge.ogg inside / outside areas / Cave BLOCKED - Waterfall, Good map for many surface types
| Wandering | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | .CFG removed music fanatic/revenge.ogg BLOCKED - Inside / Outside areas Waterfall
| Oddworld | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | Factory ruins Wind based on height
| Kmap3 | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Warm | Inside/outside areas
| Hellsgate | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Warm | Castle Ruins Inside / Outside areas + water in centre of map = swamp? mud texture not outputting as error, metal playing
| Kmap4 | Passed | Passed | Passed | Passed |  |  | ENV_Night_Warm | Castle_Ruins Inside / outside areas.
| Nudist | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script BLOCKED - Inside / Outside areas
| Dusk | Passed | Passed | Passed | Passed |  |  | ENV_Desert_Generic | BLOCKED - Inside / Outside areas mat4b (earth)
| Biologie | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Tunnels | NO XML Script
| Cellar | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Generic | NO XML Script
| B2k | Passed | Passed | Passed | Passed |  |  | ENV_Tunnels_Warm | NO XML Script Inside / Outside areas
| Metl1 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script Inside / Outside areas
| Inkedskin | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Warehouse | NO XML Script
| Gzdm1 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script Inside / Outside areas
| Aard3 | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Ventilation_Shaft | vent to centrel area, tunnels to everywhere else
| Tartech | Passed | Passed | Passed | Passed |  |  | ENV_Mountain_Cold | Inside / outside areas should be good test for water material land, footstep, bodyfall, etc..
| Zippie | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | Inside / outside areas BAD MAP - (ik_sky_day_back) - Player can go out of bounds of ground. (need to handle this some how)
Load Map > More Maps (2) | Spillway | Passed | Passed | N/A | Passed |  |  | ELM_Wind_Generic | Castle Ruins
| Fsession | Passed | Passed | N/A | Passed |  |  | ENV_Wind_Warm
| 32 | Passed | Passed | N/A | Passed |  |  | ENV_Warm_Generic | MASSIVE MAP! So many areas - inside / outside egyptsoc/stone02b (Earth) + aard/aardfdry256_1.jpg (Earth) + tech1soc/matbrown_lgt2.jpg (Earth)
| Templemount | Passed | Passed | N/A | Passed |  |  | ENV_Warm_Generic | than_ind/floor02.jpg (asigned to Concrete…. Could be metal?)
| Minion1 | Passed | Passed | N/A | Passed |  |  | ELM_Wind_Generic | Castle ruins NO XML Script
| Infertile | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | Egyptian temple
| Gdb1 | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | NO XML Script
| Aard1 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | Egyptian temple NO XML Script ik_sky_day_back - player can go out of bounds of ground. (need to handle this some how)
| Aard2 | Passed | Passed | Passed | Passed |  |  | ENV_Open_Plains_Warm | NO XML Script
| Kmap2 | Passed | Passed | N/A | Passed |  |  | ELM_Wind_Generic | NO XML Script Inside / outside areas
| Matador | Passed | Passed | N/A | Passed |  |  | ENV_Mountain_Cold | Egyptian temple - Massive! Wind height scale needed jf1/jfrock.jpg (Earth)
| Rpgcb01 | Passed | Passed | Passed | Passed |  |  | ENV_Normal_Generic_Water | NO XML Script Inside / outside areas
| Ludm1 | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | NO XML Script Inside / outside areas
| Taurus | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Generic | NO XML Script
| Ger1 | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | NO XML Script Egyptian temple Inside / Outside areas
| Dragon | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | NO XML Script Poor map textures
| Af | Passed | Passed | N/A | Passed |  |  | ELM_Wind_Generic | Sewage + warehouse af\bullet_top + af\rifle_top + af\shells_top + af\quad_top + af\rockets_top
Load Map > More Maps (3) | Kmap1 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script Egyptian Temple Inside / Outside areas
| Drianmp2 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | Inside / Outside areas
| Island_pre | Passed | Passed | Passed | Passed |  |  | ENV_Beach_Generic | All surface types Inside / outside areas (Coastal waves) NO XML script
| Style | Passed | Passed | Passed | Passed |  |  | ENV_Forest_Generic | NO XML Script Inside / Outside areas
| Hylken5 | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script
| Gib | Passed | Passed | Passed | Passed |  |  | ENV_Warehouse_Warm | NO XML Script
| Aard1_Remix | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Ventilation_Shaft | NO XML Script
| Artanis | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script
| Tongues | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Warehouse | NO XML Script
| Plagiat | Passed | Passed | Passed | Passed |  |  | ENV_Warm_Generic | NO XML Script
| Thearit | Passed | Passed | Passed | Passed |  |  | ENV_Normal_Generic_Water | NO XML Script
| Attacko | Passed | Passed | Passed | Passed |  |  | ENV_Open_Plains_Warm | NO XML Script
| Metalv2 | Passed | Passed | Passed | Passed |  |  | ENV_Ventilation_Generic | NO XML Script
| Lbase | Passed | Passed | Passed | Passed |  |  | ENV_Power_Plant_Generic | NO XML Script inside / outside
| Fox | Passed | Passed | Passed | Passed |  |  | ENV_Open_Plains_Warm | inside / outside areas
| Darth | Passed | Passed | Passed | Passed |  |  | ENV_Mountain_Cold | NO XML Script inside / outside
| Templeofdespair | Passed | Passed | Passed | Passed |  |  | ELM_Wind_Generic | NO XML Script inside / outside
SPMaps | Fanatic/Revenge | N/A | N/A | N/A | N/A |  |  | Multiple areas, waterfall, outside, inside | Castle ruins Candles and small fires (static) + Waterfall
| Dcp_the_core/enter | Passed | Passed | Passed | Passed |  |  | Power plant variations | Polish if emitter, remove scripted ambience / replace.
| Mpsp4 | N/A | N/A | N/A | N/A |  |  |  | Full test needed
| Mpsp5 | N/A | N/A | N/A | N/A |  |  |  | af\health_top2 Lava pit = find unused surface type or duplicate a surface type. Add steam one shots
| Music/Wwise201 | N/A | N/A | N/A | N/A
| Ruins | N/A | N/A | N/A | N/A |  |  |  | Waterfall
| Rampage | N/A | N/A | N/A | N/A |  |  |  | Waterfall
| Ksp1 | N/A | N/A | N/A | N/A
| Ksp2 | N/A | N/A | N/A | N/A |  |  |  | Kurt\ktrim_corner2.jpg custom
| Egysp1 | N/A | N/A | N/A | N/A
| Kksp1 | N/A | N/A | N/A | N/A
| Kartoffel | N/A | N/A | N/A | N/A
| Vaterland | N/A | N/A | N/A | N/A
| Trickjumping test! | N/A | N/A | N/A | N/A
| Mapmodel demo | N/A | N/A | N/A | N/A
SP Maps > more sp Maps | Sp_infidel | N/A | N/A | N/A | N/A
| Mpsp1 | N/A | N/A | N/A | N/A
| Mpsp2 | N/A | N/A | N/A | N/A
| Mpsp3 | N/A | N/A | N/A | N/A
| Wsg1 | N/A | N/A | N/A | N/A
| Wsg2 | N/A | N/A | N/A | N/A
| Wsg3 | N/A | N/A | N/A | N/A
| Sp_af | N/A | N/A | N/A | N/A
| Tut1 | N/A | N/A | N/A | N/A
| Camera | N/A | N/A | N/A | N/A
| Nsp3 | N/A | N/A | N/A | N/A
| Nsp2 | N/A | N/A | N/A | N/A
| Mm5remix | N/A | N/A | N/A | N/A
| Desert10 | N/A | N/A | N/A | N/A
| Cube101 | N/A | N/A | N/A | N/A
SP Maps > even more sp Maps | Cruel01 | N/A | N/A | N/A | N/A
| Cruel02 | N/A | N/A | N/A | N/A
| Sp1-test | N/A | N/A | N/A | N/A
| Tta | N/A | N/A | N/A | N/A
| Sp_stalingrad | N/A | N/A | N/A | N/A
| Kitchensink | N/A | N/A | N/A | N/A
| pigcam episode… | N/A | N/A | N/A | N/A
| Jf sp episode… | N/A | N/A | N/A | N/A
TECH / Tools | Reverb Zone 1 |  |  | Passed
| Reverb Zone 2 |  |  | Passed
| Reverb Zone 3 |  |  | Passed
| Reverb Zone 4 |  |  | Passed
| Reverb Zone 5 |  |  | Passed

## Footstep
Footsteps
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 79 | 100%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 0 | 0%
TOTAL | 79
Entity Type | Content | Status | Bug No. | Tested By | Comments
Knight | Footstep_Knight_Hard_Surface | Passed
| Footstep_Knight_Soft_Surface | Passed
| Footstep_Humanoid_Run_Stones | Passed
| Footstep_Humanoid_Metal_Run_Concrete | Passed
| Footstep_Humanoid_Metal_Run_Grass | Passed
| Footstep_Humanoid_Metal_Run_Metal | Passed
| Footstep_Humanoid_Metal_Run_Sand | Passed
| Footstep_Humanoid_Metal_Run_Rock | Passed
| Footstep_Humanoid_Metal_Run_Stone | Passed
| Footstep_Humanoid_Metal_Run_Water | Passed
| Footstep_Humanoid_Metal_Run_Wood | Passed
| Footstep_Humanoid_Metal_Run_Undergrowth | Passed
| Footstep_Humanoid_Metal_Run_Peddles | Passed
Player | Underwater_Bubbles_Generic | Passed |  |  | Underwater only
| Footstep_Generic_Water_Wades_Loop | Passed |  |  | Underwater only
| Footstep_Humanoid_Run_Concrete | Passed
| Footstep_Humanoid_Run_Grass | Passed
| Footstep_Humanoid_Run_Metal | Passed
| Footstep_Humanoid_Run_Sand | Passed
| Footstep_Humanoid_Run_Rock | Passed
| Footstep_Humanoid_Run_Stone | Passed
| Footstep_Humanoid_Run_Water | Passed
| Footstep_Humanoid_Run_Wood | Passed
| Footstep_Humanoid_Run_Undergrowth | Passed
| Footstep_Humanoid_Run_Peddles | Passed
Ogre | Footstep_Humanoid_Run_Concrete | Passed
| Footstep_Humanoid_Run_Grass | Passed
| Footstep_Humanoid_Run_Metal | Passed
| Footstep_Humanoid_Run_Sand | Passed
| Footstep_Humanoid_Run_Rock | Passed
| Footstep_Humanoid_Run_Stone | Passed
| Footstep_Humanoid_Run_Water | Passed
| Footstep_Humanoid_Run_Wood | Passed
| Footstep_Humanoid_Run_Undergrowth | Passed
| Footstep_Humanoid_Run_Peddles | Passed
Slith | Footstep_Humanoid_Run_Concrete | Passed
| Footstep_Humanoid_Run_Grass | Passed
| Footstep_Humanoid_Run_Metal | Passed
| Footstep_Humanoid_Run_Sand | Passed
| Footstep_Humanoid_Run_Rock | Passed
| Footstep_Humanoid_Run_Stone | Passed
| Footstep_Humanoid_Run_Water | Passed
| Footstep_Humanoid_Run_Wood | Passed
| Footstep_Humanoid_Run_Undergrowth | Passed
| Footstep_Humanoid_Run_Peddles | Passed
Ratamahatta | Footstep_Humanoid_Run_Concrete | Passed
| Footstep_Humanoid_Run_Grass | Passed
| Footstep_Humanoid_Run_Metal | Passed
| Footstep_Humanoid_Run_Sand | Passed
| Footstep_Humanoid_Run_Rock | Passed
| Footstep_Humanoid_Run_Stone | Passed
| Footstep_Humanoid_Run_Water | Passed
| Footstep_Humanoid_Run_Wood | Passed
| Footstep_Humanoid_Run_Undergrowth | Passed
| Footstep_Humanoid_Run_Peddles | Passed
Hellpig | Footstep_Hellpig_Run_Concrete | Passed
| Footstep_Hellpig_Run_Grass | Passed
| Footstep_Hellpig_Run_Metal | Passed
| Footstep_Hellpig_Run_Sand | Passed
| Footstep_Hellpig_Run_Rock | Passed
| Footstep_Hellpig_Run_Stone | Passed
| Footstep_Hellpig_Run_Water | Passed
| Footstep_Hellpig_Run_Wood | Passed
| Footstep_Hellpig_Run_Peddles | Passed
| Footstep_Hellpig_Run_Undergrowth | Passed
Rhino | Footstep_Rhino_Run_Concrete | Passed
| Footstep_Rhino_Run_Grass | Passed
| Footstep_Rhino_Run_Metal | Passed
| Footstep_Rhino_Run_Sand | Passed
| Footstep_Rhino_Run_Rock | Passed
| Footstep_Rhino_Run_Stone | Passed
| Footstep_Rhino_Run_Water | Passed
| Footstep_Rhino_Run_Wood | Passed
| Footstep_Rhino_Run_Peddles | Passed
| Footstep_Rhino_Run_Undergrowth | Passed
Baul | Footstep_Bauul_Run_Water_Far | Passed
| Footstep_Bauul_Run_Water_Close | Passed
| Footstep_Bauul_Run_Generic_Close | Passed
| Footstep_Bauul_Run_Generic_Far | Passed

## Magic
Magic
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 13 | 81.25%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 3 | 18.75%
TOTAL | 16
Entity Type | Content | Status | Bug No. | Tested By | Comments
Rocket Ball
Bauul | Magic_Rocket_Fire | Passed
Bauul | Magic_Rocket_Inflight | Passed
Bauul | Magic_Rocket_Impact_Close | Passed
Bauul | Magic_Rocket_Impact_Far | Passed
Bauul | Magic_Rocket_Impact_Debris | Passed
Fire Ball
Ogre | Magic_Fireball_Fire | Passed
Ogre | Magic_Fireball_Inflight | Passed
Ogre | Magic_Fireball_Impact | Passed
Ogre | Magic_Fireball_Impact_Sweetener | Passed
Ice Ball
Knight | Magic_Iceball_Fire | N/A |  |  | Not Needed
Knight | Magic_Iceball_Inflight | Passed
Knight | Magic_Iceball_Impact | Passed
Knight | Magic_Iceball_Impact_Sweetener | Passed
Slime Ball
Goblin | Magic_Slimeball_Fire | N/A |  |  | Not needed
Goblin | Magic_Slimeball_Inflight | N/A |  |  | Not Needed
Goblin | Magic_Slimeball_Impact | Passed

## Music
Music
Results
Type | Number of items | Stats
Pending | 19 | 63.33%
Passed | 9 | 30%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 2 | 6.667%
TOTAL | 30
Music Type | Content | Status | Bug No. | Tested By | Comments
Main Tracks | MUS_Game_Titles | N/A
Main Tracks | MUS_Game_Credits | N/A
Main Tracks | MUS_Game_Intro | Passed
Main Tracks | MUS_Game_Explore | Passed
Main Tracks | MUS_Game_Combat | Passed
Main Tracks | MUS_Game_Quad | Passed
Main Tracks | MUS_Game_Defeat | Passed
Main Tracks | MUS_Game_Victory | Passed
Transistion | Intro > Explore | Passed
Transistion | Intro > Combat | Passed
Transistion | Intro > Quad | Passed
Transistion | Intro > Defeat | Pending
Transistion | Intro > Victory | Pending
Transistion | Explore > Combat | Pending
Transistion | Explore > Intro | Pending
Transistion | Explore > Quad | Pending
Transistion | Explore > Defeat | Pending
Transistion | Explore > Victory | Pending
Transistion | Combat > Intro | Pending
Transistion | Combat > Explore | Pending
Transistion | Combat > Quad | Pending
Transistion | Combat > Defeat | Pending
Transistion | Combat > Victory | Pending
Transistion | Quad > Intro | Pending
Transistion | Quad > Explore | Pending
Transistion | Quad > Combat | Pending
Transistion | Quad > Defeat | Pending
Transistion | Quad > Victory | Pending
Transistion | Defeat > Intro | Pending
Transistion | Victory > Intro | Pending

## VO
VO
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 29 | 100%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 0 | 0%
TOTAL | 29
Entity Type | Content | Status | Bug No. | Tested By | Dialogue Line | Comments
Player Dialogue
| Attack 50% Health | Passed
| Death | Passed
| Secret | Passed
| Quad | Passed
| Idle 100% Health | Passed
| Idle 50% Health | Passed
The Core
| The Core - 1 Start | Passed |  |  | Listen up! You need to move through the complex to get to the evact point. You may face fierce resistence from the hostiles throughout the complex I will guide you where I can.
| The Core - 2 EnterMainComplex | Passed |  |  | Commander, you will need to find a switch to open the main door to your left.
| The Core - 3 Switch01 | Passed |  |  | Commander, this is not good! You need to locate the main control room to stop the alarm.
| The Core - 5 TopOfTunnel | Passed |  |  | Commander, you will need to find the switch to open the door to main Control room.
| The Core - 6 Switch02 | Passed |  |  | Commander, you will face fierce hostiles in the control room
| The Core - 9 EnterSideRoom | Passed |  |  | Commander, the switch to the alarm gate should be located somewhere in this next room
| The Core - 10 Switch03 | Passed |  |  | Commander, you should now have access to the alarm switch in the main control room
| The Core - 11 Switch04 | Passed |  |  | Great work Commander! You should see a bridge outside the control room window That is the route you need to take to get to the evact point Head back into the sewage tunnels and find an access point.
| The Core - 13 EnterVentiliation | Passed |  |  | Commander, there should be a back up control room to give you access to ventiliation room B
| The Core - 14 ExtVentiliation | Passed |  |  | Commander, you are looking for a switch somewhere in this room to open the gate to the ventiliation room B
| The Core - 16 Switch07 | Passed |  |  | Good work commander! You should now have access to ventiliation room B, accessed via the ventiliation chamber
| The Core - 20 ExitWallWindow | Passed |  |  | Commander, schematics suggest there are a few hidden rooms in this location. See if you can find them.
| The Core - 22 Switch13 | Passed |  |  | Commander, head back to the control room, look for access to the maintenance room there.
| The Core - 24 EnterMaintenceRoom | Passed |  |  | Almost there Commander, Locate the switches in this room to access the engine room
| The Core - 25 Switch 15 | Passed |  |  | Commander, head back to the entrance to the complex. The engine room should be found somewhere around there.
| The Core - 30 Switch19 | Passed |  |  | Watch out Commander! Fierce hostiles are blocking your exit to the evac point.
| The Core - TheCore_Alarm | Passed |  |  | Hell! Not again!
| The Core - 34 Victory | Passed |  |  | Great work Commander! The copter is on its way.
Advisor
| Generic - Map Intro | Passed
| Generic - Map Results - Victory | Passed
| Generic - Map Results - Defeat | Passed
| Generic - Player Health - Low | Passed
| Generic - Player Health - High | Passed

## Vocal
Vocalisation
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 50 | 100%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 0 | 0%
TOTAL | 50
Entity Type | Content | Status | Bug No. | Tested By | Comments
Knight | Vocal_Death_Knight_Close | Passed
| Vocal_Pain_Knight_Close | Passed
| Vocal_Grunt_Knight_Close | Passed
| Vocal_Idle_Knight_Close | Passed
| Vocal_Attack_Knight_Close | Passed
Ratamahatta | Vocal_Death_Ratamahatta_Close | Passed
| Vocal_Pain_Ratamahatta_Close | Passed
| Vocal_Grunt_Ratamahatta_Close | Passed
| Vocal_Idle_Ratamahatta_Close | Passed
| Vocal_Attack_Ratamahatta_Close | Passed
Bauul | Vocal_Death_Bauul_Close | Passed
| Vocal_Pain_Bauul_Close | Passed
| Vocal_Grunt_Bauul_Close | Passed
| Vocal_Idle_Bauul_Close | Passed
| Vocal_Attack_Bauul_Close | Passed
Rhino | Vocal_Death_Rhino_Close | Passed
| Vocal_Pain_Rhino_Close | Passed
| Vocal_Grunt_Rhino_Close | Passed
| Vocal_Idle_Rhino_Close | Passed
| Vocal_Attack_Rhino_Close | Passed
Ogre | Vocal_Death_Ogre_Close | Passed
| Vocal_Pain_Ogre_Close | Passed
| Vocal_Grunt_Ogre_Close | Passed
| Vocal_Idle_Ogre_Close | Passed
| Vocal_Attack_Ogre_Close | Passed
Hellpig | Vocal_Death_HellPig_Close | Passed
| Vocal_Pain_HellPig_Close | Passed
| Vocal_Grunt_HellPig_Close | Passed
| Vocal_Idle_HellPig_Close | Passed
| Vocal_Attack_HellPig_Close | Passed
Goblin | Vocal_Death_Goblin_Close | Passed
| Vocal_Pain_Goblin_Close | Passed
| Vocal_Grunt_Goblin_Close | Passed
| Vocal_Idle_Goblin_Close | Passed
| Vocal_Attack_Goblin_Close | Passed
Player | Vocal_Death_Player_Close | Passed
| Vocal_Pain_Player_Close | Passed
| Vocal_Grunt_Player_Close | Passed
| Vocal_Attack_Player_Close | Passed
| Vocal_Jump_Player_Close | Passed
| Vocal_Land_Player_Close | Passed
| Vocal_Land_Player_Breath_Slow | Passed
| Vocal_Land_Player_Breath_Medium | Passed
| Vocal_Land_Player_Breath_Fast | Passed
| Vocal_Land_Player_Breath_Catch | Passed
Slith | Vocal_Death_Slith_Close | Passed
| Vocal_Pain_Slith_Close | Passed
| Vocal_Grunt_Slith_Close | Passed
| Vocal_Idle_Slith_Close | Passed
| Vocal_Attack_Slith_Close | Passed

## UI
UI
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 18 | 75%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 6 | 25%
TOTAL | 24
Entity Type | Content | Status | Bug No. | Tested By | Comments
Action
| UI_Action_HeartBeat_Slow | Passed
| UI_Action_HeartBeat_Medium | Passed
| UI_Action_HeartBeat_Fast | Passed
| UI_Action_Cycle_Weapons | Passed
| UI_Action_Out_Of_Ammo | Passed
| UI_Menu_Click | N/A |  |  | Not Needed
| UI_Start_Battle | N/A |  |  | Not Needed
| UI_Item_Spawn | N/A |  |  | Not Needed
| UI_Action_Teleport | Passed
| UI_Action_Teleport_Emmitter | Passed
| UI_Action_Quad_Combat_Attacks | N/A |  |  | Not Needed
| UI_Action_Secret_Found | N/A |  |  | Not Needed
| UI_Action_Area_Indication | N/A |  |  | Not Needed
| UI_Action_Switch_Wall | Passed
| UI_Action_Switch_Lever | Passed
| UI_Action_JumpPad | Passed
| UI_Action_Spawn_Monster | Passed
| UI_Action_Spawn_Player | Passed
| UI_Action_Gate_Open_Close | Passed
| UI_Action_Gate_Open_Far | Passed
Item
| UI_Pickup_Armour | Passed
| UI_Pickup_Health_Large | Passed
| UI_Pickup_Health_Small | Passed
| UI_Pickup_Ammo | Passed

## Weapons
Weapons
Results
Type | Number of items | Stats
Pending | 0 | 0%
Passed | 26 | 100%
Failed | 0 | 0%
Not Tested | 0 | 0%
Blocked | 0 | 0%
Not Implemented | 0 | 0%
N/A | 0 | 0%
TOTAL | 26
Entity Type | Content | Status | Bug No. | Tested By | Comments
Shotgun
Player | Weaponary_Shotgun_Fire | Passed
Player | Weaponary_Shotgun_Shell_Drop_Generic | Passed
Player | Weaponary_Shotgun_Reload_Pump_In | Passed
Player | Weaponary_Shotgun_Reload_Pump_Out | Passed
Ratamahatta | Weaponary_Shotgun_Fire | Passed
Ratamahatta | Weaponary_Shotgun_Shell_Drop_Generic | Passed
Ratamahatta | Weaponary_Shotgun_Reload_Pump_In | Passed
Ratamahatta | Weaponary_Shotgun_Reload_Pump_Out | Passed
Mini Gun
Rhino | Weaponary_Mini_Gun_Fire | Passed |  |  | 2 events fired, quick succession
Machine Gun
Player | Weaponary_MachineGun_Fire | Passed
Player | Weaponary_MachineGun_Shell_Drop_Generic | Passed |  |  | Looping asset
Rifle
Player | Weaponary_Rifle_Fire | Passed
Player | Weaponary_Rifle_Reload | Passed
Player | Weaponary_Rifle_Bullet_Drop_Generic | Passed
Slith | Weaponary_Rifle_Fire | Passed
Slith | Weaponary_Rifle_Reload | Passed
Slith | Weaponary_Rifle_Bullet_Drop_Generic | Passed
Rocket Launcher
Player | Weaponary_RocketLauncher_Fire_Close | Passed
Player | Weaponary_RocketLauncher_Barrell_Turn | Passed
Player | Weaponary_RocketLauncher_Steam | Passed
Player | Projectile_Rocket_Inflight | Passed
Player | Projectile_Rocket_Impact_Close | Passed
Player | Projectile_Rocket_Impact_Far | Passed
Player | Projectile_Rocket_Impact_Debris | Passed
Melee
Player | Weaponary_Punch_Generic | Passed
Hellpig | Weaponary_Bite_Generic | Passed

## Variables
Status 1 | Status 2
Pending | Pending
Passed | Completed
Failed | In Progress
Not Tested | Blocked
Blocked | N/A
Not Implemented
N/A